## Slide 1
Second Avenue Subway TBM Drive #1
Issue: Complete TBM run by March 7
TBM Drive #1 completed February 4, ahead of the required date
February 2011
CPOC
Update
Key Issues
Notes: <number>

## Slide 2
East Side Access Systems Contracts
Issue: Reduce risks of delay
Draft Risk Assessment identified a number of risks that, if not mitigated, could lead to project delays
Actions already taken:
  Redesigned bench wall to increase production of cable installation
  Advanced bench wall, walkway, and other scope for earlier completions and reduced volume of concurrent work
  Advanced two substations to reduce testing and commissioning delay risks
  Conducting peer review of critical track installation site access plan
  Building 4-D model to confirm work plan and resolve conflicts
  Analyzing feasibility of additional work shifts; if feasible, could greatly reduce delay risks
Other risk mitigation strategies that result from the Follow-up Risk Assessment will be included in contract specs. The procurement of first Systems contract is planned to start in April with award in March-2012.
RFP procurement process allows team to evaluate and negotiate contract schedule and other terms
February 2011
CPOC
Update
Key Issues
Notes: <number>

## Slide 3
East Side Access Manhattan Caverns
Issue: Hold to recovery plan and restore schedule contingency
Actions taken to increase production:
  Contractor now working 24 hours a day, six days per week, every week (seventh day being evaluated)
  Changed running tunnel waterproofing design to simplify concrete production. This approach has been discussed with LIRR.
  Setting up additional material delivery access points in Manhattan (Wellway 3)
Progress since last report:
  Started concrete operations in W/B Cavern this month as planned
  Currently forecast start of concrete operations in E/B Cavern in April, but pushing for March start to meet plan
February 2011
CPOC
Update
Key Issues
Notes: <number>