## Slide 1
East Side Access Systems Contracts
Major Scope Items – excluding work in Harold, scope includes 70 miles of cable, nine miles of track with seven interlockings and 32 switches, new signals including five central instrument locations (CILs) and 55 switch machines, eight traction power substations, 13 facility power substations, 13 fan plants with 80 fans, communications and SCADA (automated controls)
Issue: Reduce risks of delay
Draft risk review of schedule identified a number of risks that, if not mitigated, could lead to project delays
MTACC will brief CPOC in April on the latest results from schedule risk review, including the costs of mitigation and delay
Recent actions:
  Based upon a peer review of the track installation, we have adjusted the schedule to allow second and third shifts on portions of the work where multiple contractors are not sharing tunnel access
  Additional opportunities to work multiple shifts for other work elements being explored weighing cost versus schedule benefits
  Initial 4-D model on construction sequencing nearing completion; will be used to verify schedule assumptions by the end of March
  Industry outreach meeting took place in February—well attended and generated interest in the upcoming RFP to be issued in April
  Began peer review of testing and commissioning requirements against industry practice to make sure we have appropriate requirements, given their impact on the schedule
March 2011
CPOC
Update
Key Issues
Notes: <number>

## Slide 2
East Side Access Manhattan Contracts
Issue: Hold to recovery plan and restore schedule contingency
Contractor continues 24-hour, six-day week schedule
  Despite efforts, contractor is falling short on interim milestones and has not yet recovered any lost schedule days
Cavern Concrete and Mucking Operations
  Waterproofing and formwork assembly has begun in the Westbound Cavern, with concrete placement forecast to start in April
  Contractor advancing start of waterproofing and forms in Eastbound cavern, with concrete placement forecast to start in May
  These concrete placement start forecasts match the current project schedule, but do not achieve MTACC’s goals presented at the February update to begin both caverns in March to gain back some schedule contingency
  With completion of muck removal expected by April, more parts of the cavern will be available for work
Tunnel Concrete
  Contractor will make first concrete pours in tail tracks by end of March followed by the EB4 tunnel in early April
New contractor management
  More receptive to MTA ideas and working in collaboration
  Meeting with Chairman will be scheduled for April
March 2011
CPOC
Update
Key Issues
Notes: <number>