## Slide 1
Replacement of the Queens Approach Bronx-Whitestone Bridge
Risk Assessment
<number>
Bridges & Tunnels

## Slide 2
BRONX
QUEENS
Bronx Whitestone Bridge Sequence of Major Work
Past-Present-Future
2008 – 2012
Replacement of the Bronx Approach
(BW89)
2003-2009
Suspension Span Work
Removal of Stiffening Truss
Installation of Wind Fairing
Replacement of Roadway Deck
Painting of Towers
2011 – 2014
Replacement of the Queens Approach
(BW89C)
BEYOND 2015
Suspender Rope Replacement, Main Cable Rehab. and Toll Plaza
<number>
Notes: <number>
<number>
Connects Hutchinson River Parkway, Cross Bronx Expressway and New England Thruway to Cross Island Parkway, Van Wyck Expressway, LIE, and Grand Central.

## Slide 3
Queens Approach Project Area
Transition Zone
Project Limits
<number>
Queens Anchorage
Whitestone Expressway
Cross Island Parkway

## Slide 4
Constructed in 1939
Extensive recurring needs for roadway repairs and temporary steel repairs
Narrow lanes
No shoulders
Not designed for current traffic loads
Does not meet current Seismic Standards
11’
10’
9’
Conditions: Existing Queens Approach
<number>
Notes: <number>
<number>

## Slide 5
12’
12’
12’
12’
12’
12’
NEW PIER/ROADWAY
12’ wide lanes with shoulders
Future Newly Constructed Queens Approach
<number>
REPLACEMENT OF THE ENTIRE 1,010 FT QUEENS APPROACH VIADUCT
Phase I - Construct New Foundations & Piers
  All work done under Roadway – no traffic impacts
  2011 thru Mid 2012
Phase II – Staged Replacement of Roadway while maintaining traffic
  Early 2012 – Late 2013
Phase III - Demolish existing piers/perform ground level site work
  All work under Roadway – no traffic impact
  2014
Notes: <number>
<number>

## Slide 6
<number>
Mitigation Built into Project
Lessons Learned from ongoing Bronx Approach Replacement
$10M of preparatory construction already addressed
Extensive pre-construction outreach with community, elected officials, and other City and State agencies
Utilize Traffic Enforcement Agents
Traffic mitigation measure – Temporary closure of 3rd Avenue Exit
Regional coordination of Capital Program

## Slide 7
Construction Task Budget: $240,000,000
Engineer’s Estimate: $179,000,000
Low Bid $109,000,000
Low Bid vs. Budget $131,000,000
Construction Cost Summary
<number>

## Slide 8
<number>
Risk Assessment Results (Post bid)
Construction Cost
Low Bid/ Schedule $109 M/ 42 mo
Risk Assessed ($21M/ 5mo) $130 M/ 47 mo
Project Cost
Construction, CSS, Inspection, etc. $135 M/ 42 mo
Risk Assessed ($27M/ 5 mo) $162 M/ 47 mo

## Slide 9: Probability Distribution for Remaining Total Project Escalated Cost
$162.2
Total Project Cost

## Slide 10: Major Cost Risks and Mitigations
Risk |  | Mitigation Plan
Additional costs to address mitigation of Community Sensitivities such as noise, and construction related environmental issues. |  | Continue outreach with the community and elected officials, anticipate and address mitigations, such as noise wall installations, and employ extensive site debris management.
Additional costs resulting from construction delays, such as security and traffic challenges. |  | Expedite evaluation and processing of warranted change orders related to delays eliminating any impact to construction progress/schedule. Continue to review and revise MPT staging to expedite construction.
<number>

## Slide 11: Major Schedule Risks and Mitigations
Risk |  | Mitigation Plan
Additional (or different) Maintenance of Traffic needed to accommodate traffic delays |  | Closely monitor traffic conditions and be pro-active with correction/ adjustments of MPT/ staging. Coordinate with NYCDOT and NYSDOT.
Girder placement problems (Site logistics) |  | Review and ensure Contractor’s means and methods are efficient to eliminate potential delays related to Girder placement. Use lessons learned from Bronx Approach construction.
Unanticipated structural maintenance repairs |  | Anticipate and aggressively evaluate and inspect existing structure during construction to limit/eliminate resulting delays.
<number>

## Slide 12: NEXT STEPS PRIOR TO CONSTRUCTION CONTRACT AWARD
Evaluate Bid Results
Conduct Contractor Qualification Hearing
Complete Bid Analysis and determine recommendations with respect to low bidder
<number>

## Slide 13
<number>
Bridges & Tunnels