## Slide 1: ESA Facts
<number>
  Over the past few months, we have reported on the actual and potential loss of schedule contingency (the IEC has reported that their analysis indicates that schedule contingency has been consumed) and that our confidence level in meeting the September 2016 revenue service date is low without significant mitigation
  On-going contractor delays in Manhattan and Queens
  Compressed construction schedule in Harold Interlocking has put pressure on needed Amtrak resources
  The linearity of the project (i.e. one contract has to be completed before another can start) further compresses the schedule
  Innovative approaches needed to increase our confidence level
Notes: The original design of the projects has always required that all major access needed to go through Queens. This plan has been complicated by
poor performance by the tunneling contractor in Manhattan and construction delays in Queens due to design issues.
We now face critical access issues, compressed schedules and overlapping work for follow-on contractors
The Chairman has challenged us to come up with innovative ways of overcoming these issues and develop strategies so that we can have a higher level of confidence in our ability to meet the ESA schedule
Today we want to focus on the general nature of the solutions we are working on and we will be back in September with more specifics.
<number>

## Slide 2: Solutions-”Out of the box” thinking to attack each of the problem areas!
<number>
Linearity can be mitigated with more and larger access points to the tunnels and caverns in Manhattan. Work with MNR in those areas where they may be impacted.
Evaluate with the LIRR the feasibility of re-sequencing the plans for the completion of construction, testing and commissioning and the start of revenue service
In partnership with the LIRR, evaluate the feasibility of completing the final segment of the B/C approach tunnel (one of three connections to LIRR mainline) concurrent with systems testing/commissioning
Work with LIRR and revisit assumptions for Harold construction plans
Evaluate the strategic resequencing of critical work
Notes: Some of the strategies we are looking at to improve access is to develop new areas in Manhattan for staging and bringing large material using newly constructed shafts to the caverns and tunnels below.
Provide new access/staging points in Queens for tunnel finishing and systems contractors
Key objective is to get better access to the Manhattan caverns and tunnels and allow multiple contractors to work concurrently
The B/C tunnel strategy, if feasible, has the potential to
  Relieve stress on limited Amtrak resources
  Enable both railroads to better support ESA construction within Harold/Sunnyside yard
  Save significant time if the last 1,000 feet of B/C tunnel approach can be built while testing and readiness activities in other areas are initiated
Some of the ideas we are looking at with the LIRR in terms of commissioning and pre-revenue service testing include
  Consider the use of simulators to start training earlier
  Review training requirements including number of personnel that will need to be trained before revenue service can begin
These strategies have the potential to reduce the time needed for pre-revenue service activities
Our objective in revisiting the Harold construction plans is to look at how can ESA work be done more efficiently and what are the trade offs?
In terms of the resequencing of work, we will focus on eliminating conflicting work areas, preparing sites for follow-on contractors and evaluating the reward/risks of pre-purchasing major equipment to reduce both cost and schedule risk

## Slide 3: Refinement of strategies will be presented to CPOC in September
<number>
  New approaches to access and construction phasing for ESA are very complex, need to be fully developed and evaluated with partners
  Goal of new approaches is to mitigate impacts and increase confidence of meeting Sept 2016 revenue service within available budget
  Will assess cost/schedule impacts of recommended strategies
Notes: <number>