## Slide 1
East Side Access Status Report to CPOC September 26, 2011
Notes: <number>

## Slide 2
Recap
ESA
ESA is essentially comprised of four elements—
  Manhattan tunnels, structures and station
  Queens tunnels, structures and yard
  Reconfiguration of Harold Interlocking
  Operational readiness and commissioning by the LIRR
Challenges to ESA schedule presented at previous CPOC meetings related to construction delays in Harold and Manhattan
  Delays continued through the summer, further challenging the project
Project was evaluating “out of the box” mitigations to reduce impact and maintain revenue service date
Amtrak’s recently announced Total Track Replacement program for the East River Tunnels will impact Harold work
This report will summarize the mitigation measures to date and the impact of Amtrak’s Total Track Replacement on ESA
Notes: <number>
<number>
<number>
<number>

## Slide 3
Recap
ESA
In June, committed to develop “out of the box” mitigations and report on progress to CPOC in September. These options included:
  Create new access points and strategically re-sequence critical work in Manhattan
  Examine the sequence and duration of operational readiness
  Pre-purchase critical systems equipment
  Review with LIRR the feasibility of beginning revenue service with only three of four tunnels completed
Notes: <number>
<number>
<number>
<number>

## Slide 4
Status of Manhattan Mitigation Efforts
ESA
Manhattan mitigation efforts focused on:
  Create more access points to overcome the linearity of the project
  Allow multiple contractors to work in the tunnels and caverns simultaneously
  Strategic repackaging of critical work
Notes: <number>
<number>
<number>
<number>

## Slide 5
N
Current Plan for Access
(Single-Point via Queens)
After Mitigation
(Multiple Points of Exclusive Access) – Each contract represented by a different color
Manhattan Mitigation—Create Multiple Access Points
Access from Queens
Access from Queens
37th St
44th St
50th St
55th St
Shaft 3
ESA
Notes: <number>

## Slide 6
DJ - MS#5A
DJ - MS#5A
CM012 - Precast + Finish
CM012 - Precast + Finish
Do Nothing Delay (21M)
Current Contract
Do Nothing Plan
DJ - MS#5A3 (WB)
CM012 - Precast + Finish
Access Mitigation Plan
DJ – MS#5A4 (EB)
CM020 – South of Caverns
Multiple Access Mitigation Plan
Schedule Benefit of Multiple Access Points
ESA
Mitigated Delay (12M)

## Slide 7
Ongoing efforts with LIRR to reduce the overall schedule by starting the operational readiness work prior to completing the Integrated Systems Testing
Critical Path reduction could be up to eight months
Operational Readiness Mitigation—Reduce Schedule/Timing of Activities
ESA
Notes: <number>

## Slide 8
Potential to reduce schedule and cost risks
Still under review with ESA/LIRR
Mitigation of Systems Risk – Pre-Purchasing Long Lead Items
ESA
Notes: <number>

## Slide 9: Queens – Critical Work in Harold Interlocking Always a Major Challenge for the Project
East River Tunnels
ESA
Notes: <number>

## Slide 10
Harold Mitigations
ESA
To address delays in Harold work, ESA’s project team proposed evaluating feasibility of beginning revenue service with only outside tunnels, thus allowing time for work on inner tunnels
However, evaluation of Harold mitigation has been postponed pending evaluation of impact on ESA as a result of Amtrak’s Total Track Replacement program in the East River Tunnels
  Amtrak will be completely replacing all track in East River Tunnels due to Mother’s Day derailment and other incidents that raised reliability concerns, limiting service to two tracks on weekends and requiring ESA to resequence its Harold work
  Program is fully supported by MTA
Notes: <number>
<number>
<number>
<number>

## Slide 11
Harold Mitigations
ESA
Amtrak, LIRR, and MTACC have been meeting on a regular basis to develop approach and schedule for this critical track work and minimize its impact on railroad operations and ESA construction:
  Total Track Replacement will impact areas where ESA can work
  Where possible, ESA outages will be coordinated to “piggyback” on the tunnels and track areas Amtrak will have out of service
  However, construction opportunities are limited to when ESA’s and Amtrak’s needs coincide
The project schedule will be rebaselined to capture the impacts of Amtrak work and ongoing project delays, as well as potential mitigations
Notes: <number>
<number>
<number>
<number>

## Slide 12
ESA is now analyzing the impact of the construction delays experienced to date as well as the potential impacts of Amtrak’s Track Replacement Program
Rebaselined schedule and mitigations to be developed and finalized during the 4th Quarter 2011
Goal will be to achieve a revenue service date that at a minimum meets the April 2018 Federal date that will be incorporated into the amended Full Funding Grant Agreement (FFGA) and other Federal funding commitments
  Will work closely with LIRR, Amtrak, OCO, and IEC
  Will report back to CPOC when rebaselining is complete
What’s Next?
ESA
Notes: <number>