## Slide 1
  Recap
  The IEC was directed to report their confidence in the project’s mitigation proposed in June. In response, the IEC has evaluated the viability of these mitigations with respect to schedule
  Review was undertaken before the current scope of the Amtrak East River Tunnel work was fully known
  The IEC is continuing to evaluate the impact of the East River Tunnel work and mitigation strategies as they are prepared by ESA
ESA
Notes: <number>
<number>

## Slide 2
  IEC previously reported a delay to the Revenue Service Date of September 2016, absent mitigations, due to:
    Poor performance of Manhattan contractor
    Design approval and construction delays in Harold
    Access issues for systems work in new ESA tunnels
  MTACC proposed four out-of-the-box actions to mitigate delays:
    Deliver Precast Panels for GCT Caverns through Manhattan
    Reduction of Operational Readiness Duration
    Pre-Purchasing of Systems Equipment
    Delay to B/C Approach Structures
ESA
Notes: <number>
<number>

## Slide 3
  Findings
  The mitigations reviewed by the IEC do not bring the Revenue Service Date back to September 2016.
  However, two mitigations offer benefits:
    Bringing the precast panels through Manhattan will improve access to the new ESA tunnels by reducing interference risks
    Any reduction of the operational readiness results in time savings and will improve a revised Revenue Service Date
  The costs to the project resulting from these mitigations are yet to be determined
ESA
Notes: <number>
<number>

## Slide 4
  Additional delays were identified during the review of the proposed out-of-the-box mitigations that will also need to be mitigated during the rebaselining. These delays, which are still under discussion with ESA, include:
    Access and construction duration issues for the remaining Harold third party work
    Insufficient durations for structural and systems finish-out work in Manhattan caverns
ESA
Notes: <number>
<number>

## Slide 5
  IEC Recommendations
  Include Amtrak in rebaselining effort, which considers current delays, unmitigated risks and the East River Tunnel work
  As part of the rebaselining, advance Westbound Bypass and Eastbound Reroute work to comply with high-speed rail grant requirements
  Improve the prospect of achieving the goal of a revised FFGA Revenue Service Date by:
    Forming a partnership between Amtrak and MTA to create a vehicle to incentivize Amtrak
    Strengthening LIRR’s position to lead the coordination in Harold and find a balance between customer service and construction
ESA
Notes: <number>
<number>
Talking Points:
LIRR currently leads discussions with Amtrak on balancing the risks to LIRR service with the needs of the Total Track Replacement project; in considering impacts on LIRR service, LIRR is best suited to make those judgments and should take the lead role in identifying mitigations to project delays that can appropriately consider trade-offs between customer service and construction