## Slide 1: NYCT Subway Car Program Progress Update to CPOC Michael P. Wetherell, P.E. Vice President and Chief Mechanical Officer Department of Subways November 26, 2012
,.
Notes: <number>
<footer>
<header>
07/29/26 08:29

## Slide 2
Item | Comments
Scope | 126 new ‘A’ Division cars + 380 converted R142A cars Base Order: 23 new + 10 converted cars Option Order: 103 new + 370 converted cars Provide (46) 11-car trains for Flushing CBTC / 7 Line Extension service
Schedule | Base Awarded: 5/28/2010 Option Awarded: 12/30/2011 Delivery and Conditional Acceptance Completion: 2/28/2016
Budget | Base: $116.5 M Option: $497.2 M Total: $613.7 M
Overall Status
Progress
  New single C-car scheduled to be delivered early November 2012
  As of October 18, 2012: 70 cars in production at Kawasaki’s US facilities
  Car Qualification Tests on the Base Order are 90% complete
180 Day Look Ahead
  Car Qualification Tests ongoing
  Delivery of Base Contract trains by end of 2012
  Training of RTO personnel for Qualification Testing
  Begin Unit Qualification Testing on NYCT property
Highlights
R188 Project Overview
Notes: <number>
<footer>
<header>
07/29/26 08:29

## Slide 3
R188 11-Car Configuration
R188 Train Consist
Note: The 7 Line is the only NYCT subway line that runs 11-car trains
Notes: <number>
<footer>
<header>
07/29/26 08:29

## Slide 4
R188 Delivery Schedule
Base Order deliveries complete by December 2012
First new Option train scheduled to be delivered May 2013
Eight new trains forecasted to be conditionally accepted in time for opening of 7 Line Extension
Completion of delivery of all new and converted trains scheduled for January 2016
Flushing Line CBTC forecasted completion is November 2016
Notes: <number>
<footer>
<header>
07/29/26 08:29

## Slide 5
Status | Activity | Date Needed | Issues
 Green | Delivery of new single C-car for placement within the 10 R142A conversion cars Delivery of two new trains Base Order Conditional Acceptance | Nov 2012 Dec 2012 May 2013 | Issues: None
 Green | Option Order Car Delivery Completion | Jan 2016 | Issues: None
R188 Activity and Issues
Legend
 Red - Significant impacts on Cost and/or Construction/Beneficial Date
 Yellow - Impacts that can lead to cost increase or schedule delays
 Green - No near-term impact on cost or schedule.
Notes: <number>
<footer>
<header>
07/29/26 08:29

## Slide 6
Item | Comments
Scope | 300 60-foot ‘B’ Division cars (design based on R160 cars) Will provide 36½ trains No. of 4-car units: 65 No. of 5-car units: 8
Schedule | Awarded: 6/04/2012 Delivery of test train: 12/22/2014 Delivery of 1st Production unit: 7/27/2015 Delivery Completion: 1/30/2017
Budget | $735.6 M
Overall Status
Progress
  Awarded to Bombardier Transit Corporation on June 4, 2012
  Approved Master Program Schedule
  Completion of Technical Specification Review
180 Day Look Ahead
  Preliminary Design Reviews
  In-Process Design Reviews
Highlights
R179 Project Overview
Notes: <number>
<footer>
<header>
07/29/26 08:29

## Slide 7
Item | Comments
Scope | 1,662 60-foot ‘B’ Div cars built by ALSKAW replaces older 60-foot cars Base: 660 cars Option I: 620 cars Option II: 382 cars
Schedule | Final cars delivered May 6, 2010 In Close-Out phase
Budget | Base: $1,163.0 M Option I: $1,249.2 M Option II: $842.3 M
Overall Status
Progress
  12-Month MDBF: 645,207 miles (September 2012)
  All cars off of warranty
  Assignments: NMJZQEFL
180 Day Look Ahead
  Completion of field modifications and deliverables
  Closeout Forecast for June 2013
Highlights
R160 Project Overview
Notes: <number>
<footer>
<header>
07/29/26 08:29

## Slide 8
Item | Comments
Scope | New R211 ‘B’ Division cars to replace 752 R46 cars Additional fleet growth cars (current forecast – 84 cars) Additional cars for SIR fleet replacement
Description | Next Generation design to address NYCT’s goals
Schedule | Design Master Plan approved in December 2011 2012 Award of Technical Consultant (Design Phase) RFP Negotiations Completed Request MTA Board Approval: November 2012 Award Contract: December 2012 Car Purchase Award Proposed for 2015 – 2019 Capital Program
Overall Status
R211 Future Project Overview
Notes: <number>
<footer>
<header>
07/29/26 08:29