## Slide 1: MTACC Quarterly Progress Report to CPOC East Side Access
January 27, 2014

## Slide 2: Major Construction Completed
Over $2 Billion in construction was completed in 2013 including the four major tunneling contracts in Manhattan and Queens
1

## Slide 3
Manhattan Caverns and Tunnels
Overview
43rd St
50th St
55th St
59th St
2

## Slide 4
59th St Transition
Key
3

## Slide 5
Key
53rd St Transition
50th St
53rd St
4

## Slide 6
Key
53rd St Crossover
50th St
53rd St
5

## Slide 7
Caverns
Key
6

## Slide 8
Caverns
Key
West Cavern
East Cavern
1140 ft. (Typ)
60 ft.
60 ft.
7

## Slide 9: Mined Caverns and Shafts Below Grand Central
Park
Avenue
Vanderbilt
Avenue
MNR Lower Level
MNR Upper Level
LIRR Mezzanine
Off Street
Entrances
LIRR
Concourse
Escalator
Shafts
Terminal Caverns
Upper
Platform
Lower
Platform
91’-0”
140’-0”
Freight
Elevators
Passenger
Elevators
Section Looking North
Section Looking North
19 Elevators and 50 Escalators
8

## Slide 10
43rd St Transition
43rd St
Key
9

## Slide 11
Muck Removal
Muck traveled 3.5 miles to Queens
10

## Slide 12
1.5 Million Cubic Yards of Muck Removed
East Cavern
West Cavern
Other Muck
700 feet
11
75,000 Trucks = 700+ miles (NYC to Indianapolis)

## Slide 13: Other Construction in Manhattan
Ventilation Plants:
  Facilities at 44th Street and 50th Street, worth in excess of $110M, are on target for completion during the first quarter 2014
  Facility at 55th Street is progressing on schedule, with all excavation to be completed by the end of January
Manhattan South Structures (CM005) was awarded in September and construction is progressing ahead of schedule.
12

## Slide 14: Queens – Existing Site
Queens Blvd
Honeywell St
39th St
43rd St
Thomson Ave
To Penn Station
Harold Interlocking
Yard A
Sunnyside Yard
Northern Blvd
1 mile
13

## Slide 15: Queens – Harold Interlocking
2 miles of tunneling under the busiest passenger train interlocking in the United States (~750 trains through Harold)
Four different Railroads impacted (LIRR, Amtrak, NJ Transit and NY Atlantic)
14

## Slide 16
4 Tunnels totaling 10,500 linear ft.
313 catenary poles – 60 ft. tall with 40 ft. hand dug foundations
10.7 miles of new track
95 new switches
5 new railroad bridges
26 signal towers for high tension power
15 signal bridges
15 new Signal CILs (Central Instrument Locations)
13,500 linear ft. of LIRR signal trough
Harold – Summary of Infrastructure
Hand digging foundations & rebar for catenary structure
Northern Blvd. Crossing
15

## Slide 17: Construction Highlights in Queens & Harold
Plaza Substation and Queens Structures
  includes work on the B10 Substation and in the 63rd Street tunnel in preparation for immediate turnover to the Systems contract
Active Harold Construction contracts to be completed by summer of 2014
Westbound Bypass (CH057A)
  The first High Speed Rail funded contract was awarded in November, with NTP in December
Extended Track Outages
  Under review with inputs from LIRR and Amtrak
16

## Slide 18: Next Phase of Construction is Underway
Project is transitioning from underground excavation construction to Civil/Systems construction which is MTA’s core competency
17

## Slide 19: Three Month Look Ahead
Contract awards valued at $850M following January Board meeting
  Manhattan North (CM006), Systems Facilities (CS179) and Signal Equipment procurement (VS086)
Advertise three contracts worth approximately $500M by end of first quarter 2014
  GCT Concourse and Finishes (CM014B) following an industry outreach which occurred in November
  Traction Power procurement (CS084)
  LIRR Track installation (CH057B)
Continue the Request for Expression of Interest (RFEI) for the GCT Caverns (CM007)
  Contractor submissions and interviews scheduled for February
18

## Slide 20: Supplemental Independent Review
  Update to CPOC
19
Notes: CM005 – South Structures Finish Out Work
CM006 - North Structures Finish Out Work
CM007 – GCT Caverns Finish Out Work

## Slide 21: Supplemental Independent Review
  Background
Project Budget and Revenue Service Date as established in 2012:
  $8.245 billion
  September 2019
January 2013 – Contract repackaging (CM005, CM006 & CM007) due to CM012R (Manhattan Structures) over budget
March 2013 – MTA Chairman/CEO calls for Supplemental Independent Review
  Review ESA Management/Organizational Structure
  Evaluate constructability issues (access) in Manhattan for civil and systems work
  Check Estimate on schedule and cost projections
  April 2013 – FTA/PMOC cites preliminary cost and Revenue Service Date ranges
  June 2013 to January 2014 – Supplemental Independent Review Activities
  Organizational review
  Constructability review for Manhattan and Harold
  Participation in Risk Assessments
  Project wide and Contract level analyses of schedule and budget
20
Notes: CM005 – South Structures Finish Out Work
CM006 - North Structures Finish Out Work
CM007 – GCT Caverns Finish Out Work

## Slide 22: Supplemental Independent Review
      Initial Findings/Recommendations
  Risk Profile Change
  Transition from tunnel boring & mining to systems/finishes
  Organizational changes to reflect transition from civil finish out to systems work
  Informed Repackaging Plan for Manhattan Structures Finish Out Work
  Manhattan & Harold Constructability Assessment
  Overall base schedule forecast beyond 2019
  Overall project cost forecast above $8.245B
  Critical issues with Harold operations informed schedule – ongoing review
21

## Slide 23: Management/Organizational Changes
Tone at the Top - MTAHQ is prompting change at East Side Access and endorses the following:
  ‘Executive Steering Committee’
  ESA Executive Management Team
  ESA management structure changes
  ESA reporting lines simplified
  Business Processes (Change Control, Procurement, Estimating, Scheduling) strengthened
22

## Slide 24: Proposed ESA Organizational Chart (including Capital Program oversight)
23
Technical Support
(As Needed)
IEC
MTA
Chairman/ CEO
MTA
Headquarters/ Capital Programs
Program Executive
Heavy Civil
MTA-CC
President
Senior Program Executive
MTA-CC
East Side Access
ESA EXECUTIVE STEERING COMMITTEE
Tom Prendergast Chairman, MTA
Michael Horodniceanu Member, MTACC
Helena Williams Member, LIRR
TBD Member, AMTRAK
Program Executive
Harold/Queens/ Systems & Startup
Program Executive
Project Control/ Support
Heavy Civil Construction
Harold/ Queens
Systems
LIRR & AMTRAK Working Team(s)
Construction Coordination
and Interface
Project Controls
Budget Finance and
Operations
Design Support
Contracts
Contracts
Contracts
ESA EXECUTIVE MANAGEMENT TEAM
CPOC

## Slide 25: Budget Forecast Comparisons
24
Budget Forecast Status January 2014
ESA Budget Forecast
Note:
This risk/contingency figure reflects a medium degree of mitigation (MDM)
Base Cost
Rolling Stock Reserve
Risk/Contingency
Chart: 
| MTACC | Supplemental Independent Review Consultant | Independent Engineering Consultant | FTA

Budget, B | 9.298 | 9.348 | 9.535 | 9.657
RS Reserve | 0.463
Risk | 0.395 | 0.444 | 0.4455 | 0.652

## Slide 26: Schedule Forecast Comparisons
25
Schedule Forecast Status January 2014
Note:
Supplemental Independent Review, Independent Engineering Consultant, and FTA risk/contingency number represents a medium degree of mitigation (MDM). MTACC risk/contingency is based on ‘bottom-up’ approach to establishing project schedule.
Base Schedule
Risk/Contingency
Chart: 
| MTACC | Supplemental Independent Review Consultant | Independent Engineering Consultant | FTA
Revenue Service Date | 44075 | 44501 | 44713 | 44652
 | 366 | 366 | 366 | 549



## Slide 27: RECENT and Upcoming Activities
  Management and Organizational Changes:
  - Senior Program Executive has recently been appointed
  Project Controls and Heavy Civil Program Executives have recently been appointed
  Appoint Harold/Queens Systems Program Executive
  Realize Executive Steering Committee
  Issue final Supplemental Independent Review reports on remaining tasks by end of March 2014:
  Refinement of Project Schedule and Budget
  Complete project wide and contract specific risk assessments:
  Manhattan – Systems & Harold Interlocking
26