## Slide 1: Positive Train Control Project Status
Metro-North Railroad
Long Island Rail Road
January 28, 2014 CPOC

## Slide 2: Positive Train Control Benefits
On October 16, 2008, Congress passed the Rail Safety Improvement Act of 2008 requiring implementation of PTC by Dec. 2015.
An approved PTC System must prevent the following:
  Train-to-train collisions.
  Over-speed derailments.
  Injuries to workers as the result of unauthorized incursions by train into a work zone.
  Movement of a train through an improperly aligned switch

## Slide 3: PTC System Design
PRIMARY
BACK OFFICE
ACSES SAFETY COMPUTER
Train Dispatcher
Consoles
Interlocking Signal
AutomaticSpeed Control
ACSES DATA RADIO
ADU
CSS / ATC
ACSES COMPUTER
In Track Transponders
Signal System
RAILROAD DATA NETWORK
Transponder Reader
Data Radio
Interlocking Status and Temporary Speed Restriction Radio Communications
Safety Server Transmits Temporary Speed Restrictions to Trains
Cab Signal
Signal
Location
2
ACSES II Management and Communications Systems
RWPS SYSTEM
CELLULAR
WiFi
locations
Wayside Interface Unit
ACSES II major subsystems:
On-Board (Rolling Stock)
Wayside (Interlocking and Right of Way Infrastructure)
Back Office (Temporary Speed Restriction Servers and Central Office Equipment)
Communications (Ground Based, Land Mobile Data Radio and Wireless Networks)
Roadway Worker Protection System (RWPS)
Notes: Onboard Equipment Includes:
Onboard Computers (OBC)
Data Radio
Antenna and filters (undercarriage transponder reader and roof top data radio)
Communications Manager
Power Supplies
Speed Sensors/Accelerometers
Cabling
Relays/valves
Wayside Equipment Includes:
-Wayside Interface Unit (WIU)
-Signal System Circuit Revisions for Interface (wiring, relays, microprocessors)
-Interface Cases
-Ground Based Network Equipment
-In Track Transponders
-Power Supplies
Back Office Equipment Includes:
-Safety Servers (TSR’s)
-ACSES II Messaging System
-ACSES II Network Management Servers and Equipment
-Software Maintenance Data Facility (Configuration Management and Software Development Tools)
-RWPS system
-Demilitarized Zone Equipment
-Wayside Communications Controllers
Communications Equipment Includes:
ROW Poles, Cases and Antennas/filters
Network Equipment
Communications Managers
220Mhz Data Radios
- Railroad Data Network interface equipment
- Power Supplies

## Slide 4: What PTC Does

## Slide 5: What Signaling Systems Do LIRR/MNR Have Today?
Railroads primarily rely on Automatic Speed Control (ASC) with CAB signaling
  Monitors train speed
  Maintains safe braking distance
  Maintains train separation
Exceptions:
  MNR Waterbury Branch
  LIRR segments
Railroads’ ASC Improvements
  Civil Speed Enforcement

## Slide 6: Current MNR Cab Signal System

## Slide 7: Current LIRR Signal System

## Slide 8: PTC Implementation
System Integration Contract with Joint Venture between Bombardier/Siemens.
Schedule Risks.
Pilot Testing including Roadway Worker Protection System.

## Slide 9: RWPS
PRIMARY
BACK OFFICE
ACSES SAFETY COMPUTER
Train Dispatcher
Consoles
Interlocking Signal
ACSES DATA RADIO
ADU
CSS / ATC
ACSES COMPUTER
Signal System
RAILROAD DATA NETWORK
Temporary Speed Restriction Communication
Safety Server Transmits Temporary Speed Restrictions to Trains
Signal
Location
8
ACSES II Management and Communications Systems
RWPS SYSTEM
CELLULAR
WiFi
locations
Wayside Interface Unit
EIC
EIC Portable
Cellular & WiFi
EIC Device:
-Handheld
-Laptop
-Workstation
Can be Located:
-Hi Rail Truck
-Station

## Slide 10: Meeting Compliance Date of Dec. 2015
Rail Industry Position
  Demonstrate good faith efforts
  Secretary of Transportation
    Proposal on waivers

## Slide 11: PTC Implementation Schedule and Acceleration
Current Negotiations/Targeted Schedule Improvements
  Metro-North
    Enforce Civil and Maximum Authorized Speeds from New Haven to GCT by mid-2015.
    Install PTC onboard kits on 336 M7s & 138 M3s 16 to 20 months earlier for Harlem and Hudson Lines by October 2017.
    Complete installation of PTC on all wayside segments 12 months earlier – by July 2017.
  LIRR
    Complete Installation of PTC Wayside Kits in electric territory by 12 months earlier – July 2017.
    Complete Installation of PTC On-Board Kits on 836 M-7 cars 16 months earlier by May 2017.
10

## Slide 12: MNR Targeted PTC Implementation

## Slide 13: LIRR PTC Targeted Implementation
12
Pilot 16 miles
Pilot 17 miles
Dec 31 2015
Dec 31 2016
Dec 31 2017
Dec 31 2018
63 Miles
256 Miles
314 Miles
318 Miles
380 Units
499 Units
520 Units
Wayside
OnBoard
61 Units