## Slide 1
,.
Stations Program
November 2011
Capital Program Oversight Committee
William Montanile, P.E.
Program Manager
Notes: <number>
<number>

## Slide 2

Projects in Design - 171 Stations Progress thru 3rd Quarter 2011
In Master Plan
ADA Projects (3)
Kingsbridge Rd, Hunts Point Ave, Utica Ave
In Design
Construction Forecast
2011
2012

ADA Projects (5)
23rd St, 57th St, 68th St, Ozone Park-Lefferts Blvd
Dyckman St. (Southbound only).
Rehabilitation Projects (9)
Sea Beach Line- 8thAve, Ft Hamilton, New Utrecht Ave,
18th Ave, 20th Ave, Bay Pkwy, Kings Hwy, Ave U, 86th St
2014
Component Projects (126)
126 Stations with defects rated 4 or greater
In partnership with In-house Station Maintenance Forces

2010-14

Renewal Projects (5)
Myrtle Line- Central Ave, Seneca Ave, Forest Ave,
Fresh Pond Rd, Knickerbocker Ave
2012


2011
Renewal Projects (10)
Pelham Line- Buhre, Middletown Rd, Zerega Ave, Castle Hill
Liberty Line - 104th St, Ozone Park-Lefferts Blvd, 111th St, Rockaway Blvd, 88th St, 80th St
Renewal Projects (13)
Culver Line -. Ave X, Ave U, Ave P, Bay Pkwy,
Ave I, 18 Ave, Ditmas Ave
New Lots Line - Van Siclen Ave, Pennsylvania Ave, Rockaway Ave, Saratoga Ave, Junius St, Sutter Ave


2013
2014

(1)

## Slide 3
Forecast Completion
2011
2012
2011
2012
Projects in Construction - 63 Locations Progress thru 3rd Quarter 2011
Construction Progress (Percent Complete)
Station Rehabilitation Projects: 9 locations
5 @ Brighton, Mott Ave, 3 @ Rockaway Line
Component Projects: 9 locations
Stairs @ 2 locs, Platform edges & Canopies @ 5 locs-Bwy/7th Ave,
2 @ West End
Component Projects: 3 locations
Platform Edges @3 Loc E.Pkwy Line
ADA Projects: 2 locations
Kings Hwy, Mott Ave
2011
Station Renewal: 1 location
Hunters Pt Ave-Flushing Line
86%
90%
54%
85%
10%
2012
Station Rehabilitation Projects: 23 locations
10 @ West End, 5 @ Pelham, East 180 , Dyckman St, Bleecker St
5 @ Far Rockaway
78%
Projects Recently Completed
Jay St-Metro Tech Complex , Ave U-Brighton, Columbus Circle
Complex, Neck Rd-Brighton, Street Stairs-Jamaica Line, Plat. Edge-
Myrtle Line, Plat Edge & Wall tile 86th St-4th Ave ,6 Locs Liberty Line,
Times Sq Stair, Ct Sq.-Flushing, Platform edge, @ 34th-St Bwy
& 6th Ave, Gap Fillers Ph 3.Stair @5th Ave
2011
100%
ADA Projects: 5 locations
E.180th St, Bay Pkwy, Bleecker St, Platforms 45th Rd-Ct Sq-Flushing
71st Continental
2012-13
38%
(2)
Small Business Mentoring Projects: 11 locations
7 @ New Lots Line, 3 @ Pelham Line, 1 @ Concourse Line
2012
23%
Notes: <number>

## Slide 4: Component Status thru 3rd Quarter 2011
* Defects defined as 3.0 or worse rating (5-point scale, 5 worst)
** Components include ceilings/walls, floors, columns, and thru-spans
*** Other refers to ramps, overpasses, piers, embankments, veneer facades
Notes:
53%
29%
(3)
(Excluding platform edges) **
***
72%
11%
46%
22%
58%
28%
61%
30%
61%
15%
77%
10%
61%
5%
53%
29%
Total 468 Stations
% Change
+2%
+1%
+1%
+1%
+2%

## Slide 5
Stations
Status thru 3rd Quarter 2011
Progress Toward Elimination of Defects
Total 468 Stations
Station with
More than 30%
Defects
(230)
Station with 0%
Defects
(47)
Station with
Less than 30%
Defects
(191)
Notes:
Defects defined as 3.0 or worse rating (5-point scale,
5 worst).
Recently Completed
Projects

## Slide 6
Projects Highlights
CPM – Stations Division
Stations
Status thru 3rd Quarter 2011

## Slide 7
Pelham Line Projects

## Slide 8
E.180th St. Station WPR Line

## Slide 9
Dyckman St. Station Broadway-7th Ave Line

## Slide 10
Brighton Line Projects

## Slide 11
Bleecker Street Project

## Slide 12
Station Component Projects
Platform Edge/Repairs
  Hoyt Ave
  Bergen St
  Franklin Ave
  34th St - 6th Ave & Broadway
  5 Stations Broadway Line
Historic Wall Tiles Repair
  Borough Hall-Brooklyn
Small Business Mentoring Program (SBMP)
  Stair Repair/Replace (7) Stations New Lots Line
  Stair Repair/Replace Longwood Ave Pelham Line (NB & SB)
  Stair Repair/Replace 138th-3rd Ave Pelham Line
  Stair Repair/Replace Fordham Rd Concourse Line

## Slide 13: Station Environment Program – Operating
Target Component Stations
Perform repair work, partial painting & intense cleaning
Station’s in-house forces will supplement the Capital Component Program by
performing work at:
7 Stations in 2011
  3 – Eastern Parkway Line (Hoyt Ave, Bergen St, Franklin Ave)
  4 – Pelham Line (Cypress Ave, E 143 St, E 149 St, Longwood Ave)
11 Stations in 2012
  1 – Pelham Line (138 St)
  2 – Concourse Line (Fordham Rd, 183 St)
  2 – White Plains-Jerome Ave Lines (149 St – Grand Concourse)
  5 – Broadway-7th Avenue Line (207 St, 215 St, 225 St, 238 St, 242 St)
  1 – Lexington Avenue Line (Borough Hall)
Note: Station list adjusted to level Component Program.

## Slide 14: Station Environment Program – Operating
Maintain Defect Free Rehabilitated & Renewed Stations
  This Program will preserve capital investments by timely repair of defects.*
Times Sq. Complex, Atlantic Ave Complex, Borough Hall Complex, 161st St. Yankee Stadium Complex,
149th Street/3rd Avenue, Main St, 74th St-Roosevelt Ave Complex, Union Square Complex.
Plan to expand up to 42 Stations by end of 2011 and to 60 in 2012
  2011: 4 Far Rockaway Line, 5 Brighton Line, 5 Pelham Line
  2012: 10 West End Line, 5 Far Rockaway Line,
  Dyckman St, E. 180th St., Bleecker St.
Started with 19 Stations in 2010
Added 9 newly rehabilitated stations for a total of 28
Jay St-Metro Tech Complex, Myrtle-Wyckoff Complex, 96th Street/Broadway,
Neck Road-Brighton Station, Avenue U-Brighton Station, Columbus Circle Complex
* Maintenance defects are routine and recurring needs encountered daily (such as broken tiles, loose handrails,
clogged drains, etc), while Capital defects (discussed earlier) represent remaining useful life of a component
as rated by the consultant survey.