## Slide 1: Cost Containment Working Group June 20, 2018

## Slide 2: MTA projects cost far too much and take way too long to build.
MTA’s Capital Program Challenges

## Slide 3: 3 Major Categories of Cost Drivers and Schedule Delays
UNBALANCED CONTRACTS
LAYERS OF BUREAUCRACY
WEAK PROJECT MANAGEMENT
Notes: We’ve identified at least three major categories of problems that create delays, drive our costs up, and reduce competition:
(1) Our contracts put all of the risk on contractors; and so they charge what’s become the “MTA premium” to work on our system;
(2) We weigh projects down with wasteful and time-consuming processes – sometimes intended to prevent fraud, but much of it just a way of avoiding responsibility;
(3) We don’t manage projects aggressively enough, or hold ourselves accountable for results

## Slide 4: The Problem: Unbalanced Contracts
MTA requires contractors to assume all risk on a capital project
“Worst-Case-Scenario” Bid Prices
Up to 25% “MTA Premium” Charged

## Slide 5: The Fix
Avoid “Worst Case Scenario”
Pricing by Appropriately Allocating Risk & Financial Responsibility
Expand Competition by
Permitting Flexibility in
Performance Security
Requirements
Eliminate Perceived Bias
in Dispute Resolution Process to Reduce
“MTA Premium”

## Slide 6: The Problem: Inefficiency and Layers of Bureaucracy
Inefficient Processes
Too Much Red Tape
No Accountability

## Slide 7: The Fix
Lower bid prices & expand competition
by permitting partial payments on invoices
Appoint a Project Lead - “CEO” that is
accountable for project scope, cost and
schedule with authority to veto unwarranted
Design demands and upgrades

## Slide 8
40-Step Change Order Process
As much as an 80% reduction in time to execute a change order

## Slide 9
The Problem: Weak Project Management
Inefficient Planning
Rigid Specifications
Weak Management Practices

## Slide 10: The Fix
Lower Costs with
Flexible, Performance
-Based Specifications
Lower Costs by
Incentivizing Value
Engineering
Avoid Overruns &
Delays by Applying
Value Engineering
and Risk Analysis
to Cost Forecasts
Improve Cost & Schedule
Management with
Performance-Based
Compensation and
Militant Monitoring

## Slide 11: Non-Stop Improvement
NEXT PHASE:
Examine various state laws and regulations that may require action by the Governor and State Legislature.
Work with organized labor to maximize productivity and efficiency.

## Slide 12: Moving Forward: Create a Change in Culture
Enacting Changes Now
Status Quo Not Acceptable
Continually Improve Performance
Immediately Start Evaluating Performance Metrics