## Slide 1
June 2008
MTA Proposed 2005-2009 Capital Program Amendment

## Slide 2
  Capital Programs are regularly amended, annually or semi-annually, to reflect changes in project scopes, costs or priorities
    Program changes occur within the original program envelope
  Last comprehensive 05-09 amendment approved by Board in December 06
    Last CPRB approved plan March 06
  Amendments to the 05-09 Program were suspended during development of 2008-13 accelerated program.
    In absence of Congestion Pricing, next program will follow original 10-14 period.
  Current amendment reflects impacts of regional construction market conditions and new priorities since the last amendment
    Changes in this amendment were largely anticipated in 08-13 Plan
    Program increases are offset by deferrals
    Work deferred to next program will come at a higher cost than currently budgeted.
  Presented today for consideration and comment; final amendment to be submitted at July Finance and Board meetings.
Background of Proposed Amendment

## Slide 3
  Incorporates FFGA’s for SAS and ESA previously approved by Board
    $764 million for SAS and the remaining balance of $267million for ESA (since April ‘07 Board amendment)
  Transfers funds from discontinued LaGuardia Airport Access project in 2000-2004 program
    Incorporates LGA-funded projects previously approved by Board (South Ferry, TZ Bridge Study, LMCCC and Shea station initiatives)
    Allocates remaining LGA funds to NYCT ($80 million), LIRR ($16 million) and MNR ($11 million) to fund work that would otherwise have been in next program
  CPRB approval required for these funding changes and program elements with increases greater than 10% since last CPRB approved plan (March ’06)
Proposed 2005-2009 Capital Program Amendment

## Slide 4: Proposed 2005-2009 Capital Program Amendment
Similarity in Agency Priorities and Tradeoffs
Program increases reflect higher project costs and new priority projects
  Priority given to fund projects that maximize safe service
Tradeoffs to Fund Increases
  Defer projects that were likely to occur late in the program or that are experiencing delays; reprogramming early into next program minimizes impact

## Slide 5: Proposed 2005-2009 Capital Program Amendment: New York City Transit
Major Program Increases: $2.3 b
Major Program Deferrals: $2.4 b
Cost Increases in 05-09 B Division Cars 164 Stnd Buses to Replace Artics 88 Cost Growth in 23 Stations 340 Flushing CBTC and WPR Signals 194 Culver Viaduct 93 Clara Hale Depot 221 Cost Growth in Prior Plans 198
New Projects in 05-09
B Div Growth Cars $200 m
Add’l Paratransit 33
Flood Control (LGA) 91
PA/Screens at 44 Dark Stations 47
Stations Component Prog. 50
102 Artics $54 m
19 Station Rehabs 279
Vent Plants 385 Tunnel Lighting 48
Structural Painting Projects 57
Culver Line Signals 93
QBL Interlocking 131
207th Overhaul Shop 259
Jamaica Depot 115
Ulmer and Flatbush Depots 46
Bus Radio Project 83
AVL 54
SI Track Project 36

## Slide 6: Proposed 2005-2009 Capital Program Amendment: Long Island Rail Road
Major Program Increases: $174 m
Major Program Deferrals: $141 m
Cost Increases Direct Fixation Track Repl, $14 m ERT Fire & Life Safety 10 Annual Track Programs 10 Babylon Car Wash 9 Jamaica Fit-Out (Phase 2) 8 Maint. of Way Repair Facility 5
New Projects
Flushing/Flatbush Elevators (LGA) $10m
Jamaica Capacity Study 7
M-7 Horns 7
Bridge Painting 6
Queens Village Elevators 6
Various Queens Projects (LGA) 6
WSY Substa/Tower Reloc. Design 5
Babylon to Patchogue Signals $21 m
Jamaica Interlocking Design 15
Montauk Branch bridge rehabs 12
Broadway (Port Wash. Branch) &
150th St. (Jamaica) bridge work 10
Jay Interlocking Reconfig Design 9
Penn Sta. Facilities & Yards work 5

## Slide 7: Proposed 2005-2009 Capital Program Amendment: Metro-North Railroad
Major Program Increases: $74 m
Major Program Deferrals: $43 m
Cost Increases Croton-Harmon Shop Master Plan $11m West of Hudson Locomotives (4) Mid-Life Remanufacture $7 m Cortlandt Parking– CMAQ funded 5 Poughkeepsie Station Building 4 Stewart Airport AA 3
New Projects
GCT Employee Facilities Rehab. $18 m
Bx Stas/Capacity Imprvmts (LGA) 11
Doral Hat Bldg Purch. (Beacon, NY) 2
M-2 CSR (superseded by M-8s) $10 m
Tarrytown Platform/Overpass 8
GCT Leaks Remediation 5
Croton-Harmon/Peekskill Sta. work 4
Beacon Line Undergrade bridges 3
NHL Undergrade bridge work (2) 2

## Slide 8: Proposed 2005-2009 Capital Program Amendment: Bridges and Tunnels
HenryHudson U/L TollPlaza decks $18 m
Triborough decks-Toll Plaza/Ramps 15
BBT Elect. System upgrades 11
Thrgs Nk Anch&Tower Protection 10
Thrgs Nk Orthotropic deck rehab. 9
Violations Enforcement System 9
Advanced Automated Trf. Detection 7
2nd Generation E-Zpass In-Lane 6
Belt Pkwy Ramp widening design 6
Major Program Increases: $142 m
Major Program Deferrals: $136 m
Cost Increases Brx-Whtstne Approach Decks $44 m Thrgs Nk Concrete Deck Repl. 22 Verrazano Approach Decks 19 Triborough Bldg 104 rehab. 15 BBT Ventilation rehabilitation 14 Queens Midtown building rehabs. 7
New Projects
Verrazano Structural Steel Rprs. $11 m

## Slide 9
Proposed 2005-2009 Capital Program Amendment: Capital Construction Company
Overall budget increases from $6.325 billion to $7.394 billion
  Adds remaining $267 million from FFGA to ESA ($1.255 b added in April Board amendment)
  Adds FFGA’s $764 million to SAS
Project cost growth identified in 2008-2013 Program is not reflected in amendment; will be incorporated in next capital program
Program incorporates two projects previously approved by the board, to be funded with $37.7 million from LGA to:
  Complete South Ferry Terminal ($27.3 million)
  Support MTA’s share of Lower Manhattan Construction Command Center ($10.4 million)
CPRB approval will be needed to add FFGA funds, which are critical to the progression of ESA in 2008

## Slide 10
Proposed 2005-2009 Capital Program Amendment: Inter-Agency
Re-establishes MTA Planning Element for projects previously approved by the Board, to be funded from LGA
  Shea Stadium Stations Investments ($32 million)
  Tappan Zee Bridge EIS ($28 million)

## Slide 11: Proposed 2005-2009 Capital Program Amendment
Proposal submitted for discussion and input
Final amendment will be brought to Finance Committee and Board in July
Subsequently will be submitted to CPRB for approval